## Project Info
Project Risk Management Team
Project Name:
| Name | Email
Project Manager:
Project Engineer:
Risk Plan Coordinator: (If Delegated by PM)
Financial Analyst:
Scheduler:
Monthly Update Coordinator:
Core Risk Team Members:

## Instructions
Company X Risk Plan Overview
Risk Event Description
What is the event?
A Source of a risk or hazard – the thing which has the potential to harm or assist e.g. a dangerous chemical, competitors, government.
An Event or Incident – Something that occurs such that the source of risk has the impact concerned e.g. a leak, competitor expands into or leaves your market, new or revised regulations, or some level of observation reaching a particular trigger level.
A Consequence, outcome or impact on a range of stakeholders or assets e.g. environmental damage, loss or increase of market/profits, regulations increase or decreased competitiveness
Risk Drivers
What are the conditions, actions, or events that are likely to trigger the risk event to occur or is a leading indicator to the risk event occurring?
There are two benefits to identifying risk drivers: - Focus attention on the probable root cause(s) to aid in developing a Risk Response Strategy - Identify events or trends that should be monitored
Response/ Mitigation Strategy
What action(s) will be taken to limit the likelihood of these event occurring or limiting the impacts?
Accept: | This response accepts or ignores the risk. This may be the appropriate choice when the impact or likelihood of the risk is so low that it does not warrant further attention or if you have no control whatsoever over the impact or likelihood of the risk. (e.g. the risk that your project will be terminated or be placed on hold due to a company merger).
Transfer: | This response involves moving all or part of the risk to another party. (e.g. purchase automobile insurance and transfer the risk to the insurance company, for a small monthly fee of course). Transferring risk comes with a cost.
Mitigate: | This response involves reducing the likelihood that the risk will happen, reducing the impacts of the risk or both. This is what most people are referring to when they are discussing risk management. Most risks can be mitigated with some effort. Although it is unlikely that you can reduce the impact and likelihood of occurrence to zero, this would in essence be eliminating the risk, it is often possible to significantly reduce them. For example, if you have a technical team member who is critical to the success of the project and if that person left, the project schedule would be at risk, you may be able to mitigate the risk by training a backup person to reduce the impact or offer that individual a bonus or incentive to stay reducing the likelihood of occurrence.
Avoid: | This response focuses on eliminating the risk from the project. This sounds like a great choice, so you might ask why we don’t choose this all the time. The reason, it often comes at great cost. To eliminate a risk generally requires that you remove the source of the risk from scope. For example, you may have a schedule risk associated with a new version of software that has not been released yet by the vendor. Although the customer may be expecting this software as part of their project, removal from scope would eliminate this risk.
These general response strategies can be used in combination to address a single risk event. This may be done in the event that your chosen strategy is not working effectively or as a way to attack certain types of risks. For example, you may begin by mitigating a risk reducing both the likelihood and impact. The remaining risk could then either be avoided by a smaller scope reduction, transferred to a vendor or accepted.
Contingency Plan
What action(s) will be taken if this event occurs?
Complete the “Contingency Plan” column for all risk events that the Project Manager deems necessary to adequately address the risks of the project.
The contingency plan describes what needs to be done in the event that the risk actually occurs. When the risk event actually occurs, it is no longer a risk event; it is simply an event and may require a response or plan to be activated. The project manager will need to determine what the criteria are to trigger the need for a contingency plan. One method is to use the “Total Score” column of the risk plan template to determine a threshold that requires the development of a contingency plan. For example, a total score of 85 or higher may be the threshold which triggers the need for a contingency plan to be developed. However, there may be a need to develop a contingency plan for a risk event that scores much lower due to likelihood, but has a high impact. In the end, the project manager must be comfortable with the decision around when to develop a contingency plan.
Risk Timeframe
Critical date(s) or period of exposure
Some risks are related to specific events, milestone dates or time periods. These critical dates should be documented to focus attention on the associated risk at the appropriate time.
Organizational or Cross-Project Impacts
Select "Yes" or "No"
Some risks will directly impact the Company X Organization or other Company X projects. If you feel the identified risk has this potential, Select Yes from the drop down box.
Financial Analyst and Scheduler Review
Brown and Blue Sections to the right of the 'Comments' column
All risks that have a total score of 75 or greater are required to have both a Financial Analyst (FA) review and Project Scheduler review. Although you may complete the brown and blue columns for any risks, they are required for high scoring risks. The brown columns deal with the cost. By using the dollar impact of the risk in the event that the risk occurs and the probability of occurrence, we can compute the Expected Monetary Value (EMV). The EMV is the dollar value of the risk and this value should be carried in budget contingency. What it tells you is that you should attempt to reduce or eliminate the risk, but do not spend more than the EMV amount to do so. It is helping you with the cost/benefit analysis associated with dealing with a particular risk. The blue columns deal with schedule. The project scheduler should investigate the project schedule to determine if this risk occurred would it impact the critical path, which activities would be impacted and what, if anything, can be done to build more slack in the schedule to allow for this risk or can activities be re-arranged in the schedule.

## Risk to Consider
Risk Categories to Consider
Capital Project Portfolio
1 | Funding availability (likelihood of approval)
2 | Project justification (IRR, NPV, Payback Period)
3 | Timing of the project
4 | Regulatory influence
5 | Commitment to the project
Engineering
6 | Overall project concept
7 | Scope (definition, supporting documentation, realistic goals, stability…)
8 | As-built conditions (known, assumed, documented...)
9
10 | Design (complexity, integration, past similar experience…)
11 | Configuration management
12
13
14 | Schedule (likelihood to meet agreed upon deadlines)
15 | Cost (likelihood to control the engineering cost within the agreed upon budget)
Project Management
16 | Project team composition (experience level, competence and skills, compatibility, track record…)
17 | Roles and responsibilities (established, understood, agreed…)
18 | Communication (stakeholders identified)
19 | Scope (expectations understood and agreed upon, realistic goals, stability…)
20 | Management commitment to the project
21 | Weather (impact on outdoor construction work)
22 | Past experience on a similar project (lessons learned incorporated…)
23 | Operational constraints
24 | Outage constraints (limited flexibility and opportunities, labor and contractors mandates, micro management, additional requirements…)
25 | Cost estimating (scope quality, WBS, task duration, unit costs, labor plan, outage project or not…)
26 | Scheduling (scope, WBS, task duration, dependencies, integration with outage or plant operation…)
27 | Adherence to the PMP process by all project team members
Supply Chain Management
Material
28 | Lead time
29 | Raw material (availability, cost fluctuation...)
30 | Material origin (logistics, imports…)
31 | Competitive situation
32 | Vendor performance (level of service, reliability, track record…)
33 | Technology (existing, established, new…)
34 | Schedule (likelihood to meet agreed upon deadlines…)
35 | On site storage requirements
Contracted Labor
36 | Competitive situation
37 | Vendor selection (new or well established relationship, past performance, reliability…)
38 | Availability and workload (contractor, supervision, key personnel…)
39 | Union labor (availability, productivity, skills…)
40 | Safety record
41 | Construction permits
42 | Contract terms (firm bid, T&M, …)
43 | Cost (potential for exceeding contracted labor budget…)
44 | Schedule (likelihood to meet agreed upon deadlines…)
Construction
45 | Access to site
46 | Access to equipment (lifting, rigging, scaffolding…)
47 | Weather
48 | Safety requirements
49 | Training requirements (safety and other)
50 | Labor plan (Company labor or contractor)
51 | Company labor (availability, crew consistency, productivity, …)
52 | Lay down areas
53 | Plant operational constraints (equipment availability, shut down potential…)
54 | Outage constraints (limited flexibility and opportunities, equipment availability, shut down potential…)
55 | Site conditions (soil quality…)
56 | Cost (potential for exceeding the construction budget…)
57 | Schedule (constraints, deadlines, key dependencies…)
Other
58 | Soil Assessment
59 | Excavation
60 | Planning and Coordinating with Vendors
61 | Inclement Weather
62 | Regulations and Policy
63 | Inadequate Bearing Soil Layer
64 | Working on or near Water
65 | Special Equipment Availability
66 | Improper Engineering
67 | Improperly Trained Workforce
68 | Poor Planning
69 | Communications Problems
70 | Logistics
71 | Theft
72 | Craft Shortage
73 | Permit Delay/Inspection Delay
74 | Hazardous Materials
75 | Missing/Inadequate Drawings or Specifications
76 | Scope Creep/Change Requests
77 | Late Delivery of Material/Supplies
78 | Lay down/Confined Space
79 | Contract Award Process
Information Technology
80 | Technological Advancement
81 | Poorly defined requirements
82 | Scope Creep
83 | Lack of proper organizational change management capability
84 | Improper Testing or testing taking longer than expected
85 | Data Quality Issues
86
87 | Software Development Delays
88 | Inadequate training of end users

## Impacts Defined
Risk impact level Matrix
Likelihood | Low |  | Medium |  |  | High
| Unlikely |  | Likely |  |  | Almost Certain
Impacts | Low |  | Medium |  |  | High
Schedule | No Impact to Critical Path or Field Work |  | Potential to Affect Critical Path or Field Work |  |  | Certain to Affect Critical Path or Field Work
Cost | Less Than | 10000 | 10000 | to | 50000 | Greater Than | 50000
Quality | Minor impact to product deliverables |  | Moderate impact to product deliverables |  |  | Major impact to product deliverables
Safety | No Impact to worker safety |  | Minor impact to worker safety |  |  | Major impact to worker safety
Scope | < 1% |  | 2% to 5% |  |  | > 5%

## Risk Register
[30 empty] | Event Did not Occur / No Action Taken | 0
[30 empty] | Event Did not Occur / Mitigation Successful | 0
[30 empty] | Risk Transferred | 0
[30 empty] | Risk Avoided | 0
[27 empty] | Critical Path |  |  | Risk Accepted | 0
|  |  | H | [17 empty] | Default |  | Default |  |  |  | Near Critical Path | Risk Accepted |  | Event Occurred - Impacts Mitigated | 0
|  |  | M | [11 empty] | Yes | [5 empty] | FA Input |  | FA Input |  |  |  | Non-Critical Path | Built into Schedule |  | Event Occurred - Treatment Ineffective | 0
|  |  | L | [11 empty] | No | [5 empty] | PM input |  | PM input | [6 empty] | Duplicate / Combined with Other Risk | 0
[21 empty] | PE Input |  | PE Input
Project Name: MPP FGD Unit 1 & Unit 2 | [15 empty] | Date: ##/##/## | [14 empty] | Date: ##/##/##
|  |  |  | Impacts | [14 empty] | Financial Analysis | [6 empty] | Schedule Analysis |  |  |  | Risk Closure
# | Risk Event Description What is the event? | Category Sub-project, Project Phase, Location etc. (Optional) | Likelihood | Schedule | Cost | Quality | Safety | Scope | Total Score | Risk Event Drivers What are the conditions, actions, or events that are likely to trigger the risk event to occur or is a leading indicator to the risk event occurring? | Response/ Mitigation Strategy What action(s) will be taken to limit the likelihood of these event occurring or limiting the impacts? | Contingency Plan What action(s) will be taken if this event occurs? | Owner | Risk Timeframe Critical date(s) or period of exposure | Organizational or Cross-Project Impacts | Comments | Status | Color | FA Review Required? | $ Impact | Source | Probability | Source | Expected Monetary Value (EMV) | FA Comments | Scheduler Review Required? | Critical Path ? | Scheduler Response | Scheduler Comments (Activity #, Quntified impact etc.) | Closure Statement | Notes / Lessons Learned
1 | (Example) There may be an insufficient number of skilled internal technical resources available to support the development of the new system which will impact schedule and cost. | Development | H | H | H | M | L | L | 75 | Drivers to monitor: - Development schedules slips - Excessive overtime is needed to keep pace with the schedule - High number of quality errors discovered during the testing cycle Drivers that have occurred: - | Planned Actions: - Train additional internal resources - Hire additional contractors - Add contingency to the budget to allow for overtime work Completed Actions: - Train additional internal technical resources | Planned Actions: - Outsource portions of the development to an outside vendor - Adjust project schedule and budget | Jane Smith | 3/1/11 - 6/30/11 | Yes |  | !OPEN | RED | Y |  | Default |  | Default | 0 |  | Y
2 |  |  | L | L | L | L | L | L | 5 | Drivers to monitor: - Drivers that have occurred: - | Planned Actions: - - Completed Actions: - | Planned Actions: - - |  |  | No |  | !OPEN | Green | N |  | Default |  | Default | 0 |  | N
3 |  |  | L | L | L | L | L | L | 5 | Drivers to monitor: - Drivers that have occurred: - | Planned Actions: - - Completed Actions: - | Planned Actions: - - |  |  | No |  | !OPEN | Green | N |  | Default |  | Default | 0 |  | N
4 |  |  | L | L | L | L | L | L | 5 | Drivers to monitor: - Drivers that have occurred: - | Planned Actions: - - Completed Actions: - | Planned Actions: - - |  |  | No |  | !OPEN | Green | N |  | Default |  | Default | 0 |  | N
5 |  |  | L | L | L | L | L | L | 5 | Drivers to monitor: - Drivers that have occurred: - | Planned Actions: - - Completed Actions: - | Planned Actions: - - |  |  | No |  | !OPEN | Green | N |  | Default |  | Default | 0 |  | N
6 |  |  | L | L | L | L | L | L | 5 | Drivers to monitor: - Drivers that have occurred: - | Planned Actions: - - Completed Actions: - | Planned Actions: - - |  |  | No |  | !OPEN | Green | N |  | Default |  | Default | 0 |  | N
7 |  |  | L | L | L | L | L | L | 5 | Drivers to monitor: - Drivers that have occurred: - | Planned Actions: - - Completed Actions: - | Planned Actions: - - |  |  | No |  | !OPEN | Green | N |  | Default |  | Default | 0 |  | N
8 |  |  | L | L | L | L | L | L | 5 | Drivers to monitor: - Drivers that have occurred: - | Planned Actions: - - Completed Actions: - | Planned Actions: - - |  |  | No |  | !OPEN | Green | N |  | Default |  | Default | 0 |  | N
9 |  |  | L | L | L | L | L | L | 5 | Drivers to monitor: - Drivers that have occurred: - | Planned Actions: - - Completed Actions: - | Planned Actions: - - |  |  | No |  | !OPEN | Green | N |  | Default |  | Default | 0 |  | N
| Closed Risks | [15 empty] | !Ox |  | Closed Risks
1 |  |  | L | L | L | L | L | L | 5 | Drivers to monitor: - Drivers that have occurred: - | Planned Actions: - - Completed Actions: - | Planned Actions: - - |  |  | No |  | !OPEN | Green | N |  | Default |  | Default | 0 |  | N
1 |  |  | L | L | L | L | L | L | 5 | Drivers to monitor: - Drivers that have occurred: - | Planned Actions: - - Completed Actions: - | Planned Actions: - - |  |  | No |  | !OPEN | Green | N |  | Default |  | Default | 0 |  | N
1 |  |  | L | L | L | L | L | L | 5 | Drivers to monitor: - Drivers that have occurred: - | Planned Actions: - - Completed Actions: - | Planned Actions: - - |  |  | No |  | !OPEN | Green | N |  | Default |  | Default | 0 |  | N
1 |  |  | L | L | L | L | L | L | 5 | Drivers to monitor: - Drivers that have occurred: - | Planned Actions: - - Completed Actions: - | Planned Actions: - - |  |  | No |  | !OPEN | Green | N |  | Default |  | Default | 0 |  | N
1 |  |  | L | L | L | L | L | L | 5 | Drivers to monitor: - Drivers that have occurred: - | Planned Actions: - - Completed Actions: - | Planned Actions: - - |  |  | No |  | !OPEN | Green | N |  | Default |  | Default | 0 |  | N
Open Item
Completed Activity

## Applies to All (hidden)
H
M
L
AMI Project: Risk Plan | [15 empty] | Date: 01/27/2010
Applies to All Project List
# | Risk Event Description What is the event? | Applies to All | Likelihood | Impacts |  |  |  |  | Total Score | Risk Event Drivers What are the conditions, actions, or events that are likely to trigger the risk event to occur or is a leading indicator to the risk event occurring? |  | Response/ Mitigation Strategy What action(s) will be taken to limit the likelihood of these event occurring or limiting the impacts? | Contingency Plan What action(s) will be taken if this event occurs? | Owner | Risk Timeframe Critical date(s) or period of exposure | Comments | ●
|  |  |  | Schedule | Cost | Quality | Safety | Scope | [8 empty] | √
68 | Corporate financial position changes and does not support project execution plan | Y | H | H | M | L | L | H | 75 | ● |  | ● | ● | Norlin
4 | System integration scope is not well defined | Y | H | L | H | H | L | M | 75 | ● |  | √ | ● | Melton
3 | System integration costs are higher than expected | Y | H | L | H | H | L | M | 75 | ● |  | √ | ● | Melton |  | Combine 3&4?
1 | Project may not be funded to end and benefits may not be realized | Y | H | H | M | L | L | H | 75 | ● |  | ● | ● | Norlin
97 | Inadequate # of IT human resources to support the project (project & operations) | Y | H | H | L | M | L | L | 55 | ● |  | ● | ● | Norlin
53 | Required firmware/software upgrade negatively impacts production devices | Y | M | H | H | H | L | L | 51 | ● |  | ● | ● | Moccia
86 | Operational business units / contractors not staffed properly to support project | Y | H | M | L | M | L | L | 45 | ● |  | ● | ● | Norlin
55 | Lack of adequate vendor documentation | Y | H | M | L | M | L | L | 45 | ● |  | ● | ● | Moccia
87 | AMI failures or problems at other utility adversely affects project | Y | M | H | M | M | L | L | 39 | ● |  | ● | ● | Sitkauskas
6 | MPSC disallows a component of the plan impacting benefit realization or cost recovery(example: remote disconnect) | Y | M | M | H | L | L | M | 39 | ● |  | ● | ● | Sitkauskas
57 | Organization human resources not adequate to accept and utilize as required (too busy, other focus) | Y | H | M | L | L | L | L | 35 | ● |  | ● | ● | Sitkauskas
49 | Catastrophic storm occurs impacting Communications (meters to AMI) | Y | H | M | L | L | L | L | 35 | ● |  | ● | ● | Switala
48 | Catastrophic storm occurs impacting rollout schedule | Y | H | M | L | L | L | L | 35 | ● |  | ● | ● | Jamerson
105 | Higher than expected work required at customer site due to aging infrastructure | Y | M | L | M | L | M | L | 27 | ● |  | ● | ● | Jamerson
101 | Failure to follow proper installation procedures impacts customers | Y | M | L | L | M | M | L | 27 | ● |  | ● | ● | Jamerson
100 | Higher than expected inclement weather conditions | Y | M | M | L | L | M | L | 27 | ● |  | ● | ● | Jamerson
96 | Inadequately defined design freeze date & procedure | Y | M | M | L | L | L | M | 27 | ● |  | ● | ● | Melton
95 | Later than expected IT system change | Y | M | M | L | L | L | M | 27 | ● |  | ● | ● | Melton
94 | Higher than anticipated number of IT system changes | Y | M | M | L | L | L | M | 27 | ● |  | ● | ● | Melton
78 | Loss of key personnel without effective knowledge transfer or replacement (DTE & Contractors) | Y | M | M | L | M | L | L | 27 | ● |  | ● | ● | Sitkauskas
59 | Future state business processes not properly defined prior to milestone date | Y | M | L | M | M | L | L | 27 | ● |  | ● | ● | McCormick
56 | Discover a problem in the field that was not anticipated causing cost and schedule overruns | Y | M | M | M | L | L | L | 27 | ● |  | ● | ● | Switala
7 | Security vulnerability discovered with outward equipment(meters, cell relays, home area network, other) | Y | M | M | L | M | L | L | 27 | ● |  | ● | ● | Melton
104 | DTE may not have adequate diagnostic tools to support post-meter installation | Y | H | L | L | L | L | L | 25 | ● |  | ● | ● | Switala
58 | Ineffective change management strategy Leads to low employee engagement | Y | M | L | L | M | L | L | 21 | ● |  | ● | ● | Sitkauskas |  | May affect ability to realize benefits
2 | New firmware technology does not perform to specifications | Y | M | M | L | L | L | L | 21 | ● |  | ● | ● | Melton
16 | Itron is acquired by a competitor which leads to technology change | Y | L | H | H | M | L | H | 19 | ● |  | ● | ● | Kret
15 | Itron goes out of business / defaults on contract | Y | L | H | H | M | L | H | 19 | ● |  | ● | ● | Kret
8 | Security breach takes place with outward equipment(meters, cell relays, home area network, other) | Y | L | H | H | H | L | M | 19 | ● |  | ● | ● | Melton |  | Safety is M for SmartCircuits
108 | Significant schedule delay may result in technology obsolescence | Y | L | M | H | M | L | M | 15 | ● |  | ● | ● | Norlin
102 | Customer complaints may be higher than expected | Y | M | L | L | L | L | L | 15 | ● |  | ● | ● | Jamerson
98 | Ineffective stakeholder engagement | Y | M | L | L | L | L | L | 15 | ● |  | ● | ● | Norlin
73 | Installation causes higher levels of property damage than projected | Y | M | L | L | L | L | L | 15 | ● |  | ● | ● | Jamerson
61 | Takes longer than anticipated for Operations to understand and effectively utilize new technology & processes | Y | M | L | L | L | L | L | 15 | ● |  | ● | ● | McCormick
39 | DOE payments to DTE come in later than expected. | Y | M | L | L | L | L | L | 15 | ● |  | ● | ● | Hull
83 | Project cost is grossly underestimated | Y | L | M | H | L | L | M | 13 | ● |  | ● | ● | Norlin
70 | DOE terminates grant for convenience | Y | L | H | H | L | L | L | 13 | ● |  | ● | ● | Hull |  | Would return to original project plan pre-DOE
34 | DOE grant is not executed - Never reach agreement | Y | L | H | H | L | L | L | 13 | ● |  | ● | ● | Hull |  | Scope =H for other projects
81 | Higher than expected failure rates of meters | Y | L | M | L | H | L | L | 11 | ● |  | ● | ● | Kret
43 | Itron may not be able to keep up with the schedule | Y | L | H | M | L | L | L | 11 | ● |  | ● | ● | Jamerson
42 | Itron may not provide materials according to the schedule | Y | L | H | M | L | L | L | 11 | ● |  | ● | ● | Kret
17 | Itron could introduce security risk into product | Y | L | M | H | L | L | L | 11 | ● |  | ● | ● | Moccia
9 | DTE employee misuse role resulting in sabotage | Y | L | M | H | L | L | L | 11 | ● |  | ● | ● | McCormick
107 | Lack of effective Testing Plan | Y | L | M | L | M | L | L | 9 | ● |  | ● | ● | Moccia
84 | Itron system fails to perform according to standards | Y | L | M | L | M | L | L | 9 | ● |  | ● | ● | Moccia
82 | DOE(or other Federal) rule change impacts project execution plan | Y | L | M | M | L | L | L | 9 | ● |  | ● | ● | Hull
80 | New technology standards require infrastructure change | Y | L | M | M | L | L | L | 9 | ● |  | ● | ● | Melton
79 | Communication technology may change impacting meter operation / communication(AT&T) | Y | L | M | M | L | L | L | 9 | ● |  | ● | ● | Melton
72 | Union employees go on strike | Y | L | M | L | L | M | L | 9 | ● |  | ● | ● | Jamerson
65 | DOE rejects customer behavior study plan | Y | L | M | L | M | L | L | 9 | ● |  | ● | ● | Hull |  | Hull: Review Impacts
64 | DOE rejects risk analysis/benefits plan | Y | L | M | L | M | L | L | 9 | ● |  | ● | ● | Hull |  | Hull: Review Impacts
63 | DOE rejects project execution | Y | L | M | L | M | L | L | 9 | ● |  | ● | ● | Hull |  | Hull: Review Impacts
62 | DOE rejects cyber security plan | Y | L | M | L | M | L | L | 9 | ● |  | ● | ● | Hull |  | Hull: Review Impacts
52 | Single point vulnerability with communications architecture | Y | L | L | M | L | L | M | 9 | ● |  | ● | ● | Melton
38 | Supply chain does not do proper debarment due diligence | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Kret
37 | Supply chain does not include necessary flow-down provisions to vendors | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Kret
36 | DOE audit disallows some costs | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
35 | Unanticipated action related to Davis-Bacon Act | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
33 | Improper costs are included in DOE accounting | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
32 | Time keeping for DOE reporting is inaccurate or incorrect | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
31 | DTE time keeping system cannot provide necessary information for DOE Reporting | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
30 | Accounting for DOE reporting is inaccurate or incorrect | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
29 | DTE accounting system cannot provide necessary information for DOE Reporting | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
28 | Vendors do not provide in kind-services (Cost share) | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
27 | Terms of DOE grant are violated | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
26 | Vendors / contractors do not provide timely info for DOE Reporting | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
25 | Vendors / contractors do not provide proper info for DOE Reporting | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
24 | DOE Reporting is not completed in a timely manner | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
23 | Report to DOE is inaccurate | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull |  | Regardless of Rating DOE related Items need to be closely tracked.
22 | Third party claims that the technology we are using violates a patent or trade secret | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Kret
110 | Project does not take appropriate steps to maintain confidentiality of Customer data | Y | L | L | M | L | L | L | 7 |  |  |  |  | Hull |  | Would affect company not necessarily the project
60 | Project Team not adequately trained in new processes & technology | Y | L | L | L | M | L | L | 7 | ● |  | ● | ● | Switala
51 | Installer commits crime/fraud in the field | Y | L | L | L | L | M | L | 7 | ● |  | ● | ● | Jamerson
50 | Safety incident occurs resulting in process change or training | Y | L | L | L | L | M | L | 7 | ● |  | ● | ● | Jamerson
40 | Contractor/sub-contractor fails DOE audit | Y | L | L | M | L | L | L | 7 | ● |  | ● | ● | Kret
18 | Interveners or grassroots groups negatively impact customer opinions | (SH) | L | L | L | L | L | L | 5 | ● |  | ● | ● | Sitkauskas
12 | DTE call center volume may increase due to 5,000 meter changes per day increasing wait time significantly | (SH) | L | L | L | L | L | L | 5 | ● |  | ● | ● | McCormick
91 | Negative media as a result of ineffective employment communications | Y | L | L | L | L | L | L | 5 | ● |  | ● | ● | Sitkauskas
67 | Communication plan with regulators is inadequate (does not explain benefits and detriments of the system) | Y | L | L | L | L | L | L | 5 | ● |  | ● | ● | Sitkauskas |  | Regardless of rating this issue should be tracked closely
66 | Communication plan with customers is inadequate (does not explain benefits and detriments of the system) | Y | L | L | L | L | L | L | 5 | ● |  | ● | ● | Sitkauskas |  | Regardless of rating this issue should be tracked closely
21 | Prolonged data center outage impacts AMI system | Y | L | L | L | L | L | L | 5 | ● |  | ● | ● | Melton
106 | Lack of effective Quality Management Plan | Y | [6 empty] | 0 | ● |  | ● | ● | Stasek |  | See # 88
93 | Project or vendor scope is not adequately defined | Y | [6 empty] | 0 | ● |  | ● | ● | Norlin |  | See # 88
88 | Inadequate project management | Y | [6 empty] | 0 | ● |  | ● | ● | Norlin |  | Need to expand
120 | [8 empty] | 0 | ● |  | ● | ●
119 | [8 empty] | 0 | ● |  | ● | ●
118 | [8 empty] | 0 | ● |  | ● | ●
117 | [8 empty] | 0 | ● |  | ● | ●
116 | [8 empty] | 0 | ● |  | ● | ●
115 | [8 empty] | 0 | ● |  | ● | ●
114 | [8 empty] | 0 | ● |  | ● | ●
113 | [8 empty] | 0 | ● |  | ● | ●
112 | [8 empty] | 0 | ● |  | ● | ●
Legend
[10 empty] | ● | Open Item
[10 empty] | √ | Completed Activity

## Applies to All (Printable) (hidden)
AMI Project: Risk Plan | [15 empty] | Date: 01/27/2010
Identified Risks that Apply to All Smart Current Projects
# | Risk Event Description What is the event? | Applies to All | Likelihood | Impacts |  |  |  |  | Total Score | Risk Event Drivers What are the conditions, actions, or events that are likely to trigger the risk event to occur or is a leading indicator to the risk event occurring? |  | Response/ Mitigation Strategy What action(s) will be taken to limit the likelihood of these event occurring or limiting the impacts? | Contingency Plan What action(s) will be taken if this event occurs? | Owner | Risk Timeframe Critical date(s) or period of exposure | Comments | ●
|  |  |  | Schedule | Cost | Quality | Safety | Scope | [8 empty] | √
68 | Corporate financial position changes and does not support project execution plan | Y | H | H | M | L | L | H | 75 | ● |  | ● | ● | Norlin
4 | System integration scope is not well defined | Y | H | L | H | H | L | M | 75 | ● |  | √ | ● | Melton
3 | System integration costs are higher than expected | Y | H | L | H | H | L | M | 75 | ● |  | √ | ● | Melton |  | Combine 3&4?
1 | Project may not be funded to end and benefits may not be realized | Y | H | H | M | L | L | H | 75 | ● |  | ● | ● | Norlin
97 | Inadequate # of IT human resources to support the project (project & operations) | Y | H | H | L | M | L | L | 55 | ● |  | ● | ● | Norlin
53 | Required firmware/software upgrade negatively impacts production devices | Y | M | H | H | H | L | L | 51 | ● |  | ● | ● | Moccia
86 | Operational business units / contractors not staffed properly to support project | Y | H | M | L | M | L | L | 45 | ● |  | ● | ● | Norlin
55 | Lack of adequate vendor documentation | Y | H | M | L | M | L | L | 45 | ● |  | ● | ● | Moccia
87 | AMI failures or problems at other utility adversely affects project | Y | M | H | M | M | L | L | 39 | ● |  | ● | ● | Sitkauskas
6 | MPSC disallows a component of the plan impacting benefit realization or cost recovery(example: remote disconnect) | Y | M | M | H | L | L | M | 39 | ● |  | ● | ● | Sitkauskas
57 | Organization human resources not adequate to accept and utilize as required (too busy, other focus) | Y | H | M | L | L | L | L | 35 | ● |  | ● | ● | Sitkauskas
49 | Catastrophic storm occurs impacting Communications (meters to AMI) | Y | H | M | L | L | L | L | 35 | ● |  | ● | ● | Switala
48 | Catastrophic storm occurs impacting rollout schedule | Y | H | M | L | L | L | L | 35 | ● |  | ● | ● | Jamerson
105 | Higher than expected work required at customer site due to aging infrastructure | Y | M | L | M | L | M | L | 27 | ● |  | ● | ● | Jamerson
101 | Failure to follow proper installation procedures impacts customers | Y | M | L | L | M | M | L | 27 | ● |  | ● | ● | Jamerson
100 | Higher than expected inclement weather conditions | Y | M | M | L | L | M | L | 27 | ● |  | ● | ● | Jamerson
96 | Inadequately defined design freeze date & procedure | Y | M | M | L | L | L | M | 27 | ● |  | ● | ● | Melton
95 | Later than expected IT system change | Y | M | M | L | L | L | M | 27 | ● |  | ● | ● | Melton
94 | Higher than anticipated number of IT system changes | Y | M | M | L | L | L | M | 27 | ● |  | ● | ● | Melton
78 | Loss of key personnel without effective knowledge transfer or replacement (DTE & Contractors) | Y | M | M | L | M | L | L | 27 | ● |  | ● | ● | Sitkauskas
59 | Future state business processes not properly defined prior to milestone date | Y | M | L | M | M | L | L | 27 | ● |  | ● | ● | McCormick
56 | Discover a problem in the field that was not anticipated causing cost and schedule overruns | Y | M | M | M | L | L | L | 27 | ● |  | ● | ● | Switala
7 | Security vulnerability discovered with outward equipment(meters, cell relays, home area network, other) | Y | M | M | L | M | L | L | 27 | ● |  | ● | ● | Melton
104 | DTE may not have adequate diagnostic tools to support post-meter installation | Y | H | L | L | L | L | L | 25 | ● |  | ● | ● | Switala
58 | Ineffective change management strategy Leads to low employee engagement | Y | M | L | L | M | L | L | 21 | ● |  | ● | ● | Sitkauskas |  | May affect ability to realize benefits
2 | New firmware technology does not perform to specifications | Y | M | M | L | L | L | L | 21 | ● |  | ● | ● | Melton
16 | Itron is acquired by a competitor which leads to technology change | Y | L | H | H | M | L | H | 19 | ● |  | ● | ● | Kret
15 | Itron goes out of business / defaults on contract | Y | L | H | H | M | L | H | 19 | ● |  | ● | ● | Kret
8 | Security breach takes place with outward equipment(meters, cell relays, home area network, other) | Y | L | H | H | H | L | M | 19 | ● |  | ● | ● | Melton |  | Safety is M for SmartCircuits
108 | Significant schedule delay may result in technology obsolescence | Y | L | M | H | M | L | M | 15 | ● |  | ● | ● | Norlin
102 | Customer complaints may be higher than expected | Y | M | L | L | L | L | L | 15 | ● |  | ● | ● | Jamerson
98 | Ineffective stakeholder engagement | Y | M | L | L | L | L | L | 15 | ● |  | ● | ● | Norlin
73 | Installation causes higher levels of property damage than projected | Y | M | L | L | L | L | L | 15 | ● |  | ● | ● | Jamerson
61 | Takes longer than anticipated for Operations to understand and effectively utilize new technology & processes | Y | M | L | L | L | L | L | 15 | ● |  | ● | ● | McCormick
39 | DOE payments to DTE come in later than expected. | Y | M | L | L | L | L | L | 15 | ● |  | ● | ● | Hull
83 | Project cost is grossly underestimated | Y | L | M | H | L | L | M | 13 | ● |  | ● | ● | Norlin
70 | DOE terminates grant for convenience | Y | L | H | H | L | L | L | 13 | ● |  | ● | ● | Hull |  | Would return to original project plan pre-DOE
34 | DOE grant is not executed - Never reach agreement | Y | L | H | H | L | L | L | 13 | ● |  | ● | ● | Hull |  | Scope =H for other projects
81 | Higher than expected failure rates of meters | Y | L | M | L | H | L | L | 11 | ● |  | ● | ● | Kret
43 | Itron may not be able to keep up with the schedule | Y | L | H | M | L | L | L | 11 | ● |  | ● | ● | Jamerson
42 | Itron may not provide materials according to the schedule | Y | L | H | M | L | L | L | 11 | ● |  | ● | ● | Kret
17 | Itron could introduce security risk into product | Y | L | M | H | L | L | L | 11 | ● |  | ● | ● | Moccia
9 | DTE employee misuse role resulting in sabotage | Y | L | M | H | L | L | L | 11 | ● |  | ● | ● | McCormick
107 | Lack of effective Testing Plan | Y | L | M | L | M | L | L | 9 | ● |  | ● | ● | Moccia
84 | Itron system fails to perform according to standards | Y | L | M | L | M | L | L | 9 | ● |  | ● | ● | Moccia
82 | DOE(or other Federal) rule change impacts project execution plan | Y | L | M | M | L | L | L | 9 | ● |  | ● | ● | Hull
80 | New technology standards require infrastructure change | Y | L | M | M | L | L | L | 9 | ● |  | ● | ● | Melton
79 | Communication technology may change impacting meter operation / communication(AT&T) | Y | L | M | M | L | L | L | 9 | ● |  | ● | ● | Melton
72 | Union employees go on strike | Y | L | M | L | L | M | L | 9 | ● |  | ● | ● | Jamerson
65 | DOE rejects customer behavior study plan | Y | L | M | L | M | L | L | 9 | ● |  | ● | ● | Hull |  | Hull: Review Impacts
64 | DOE rejects risk analysis/benefits plan | Y | L | M | L | M | L | L | 9 | ● |  | ● | ● | Hull |  | Hull: Review Impacts
63 | DOE rejects project execution | Y | L | M | L | M | L | L | 9 | ● |  | ● | ● | Hull |  | Hull: Review Impacts
62 | DOE rejects cyber security plan | Y | L | M | L | M | L | L | 9 | ● |  | ● | ● | Hull |  | Hull: Review Impacts
52 | Single point vulnerability with communications architecture | Y | L | L | M | L | L | M | 9 | ● |  | ● | ● | Melton
38 | Supply chain does not do proper debarment due diligence | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Kret
37 | Supply chain does not include necessary flow-down provisions to vendors | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Kret
36 | DOE audit disallows some costs | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
35 | Unanticipated action related to Davis-Bacon Act | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
33 | Improper costs are included in DOE accounting | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
32 | Time keeping for DOE reporting is inaccurate or incorrect | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
31 | DTE time keeping system cannot provide necessary information for DOE Reporting | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
30 | Accounting for DOE reporting is inaccurate or incorrect | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
29 | DTE accounting system cannot provide necessary information for DOE Reporting | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
28 | Vendors do not provide in kind-services (Cost share) | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
27 | Terms of DOE grant are violated | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
26 | Vendors / contractors do not provide timely info for DOE Reporting | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
25 | Vendors / contractors do not provide proper info for DOE Reporting | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
24 | DOE Reporting is not completed in a timely manner | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull
23 | Report to DOE is inaccurate | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Hull |  | Regardless of Rating DOE related Items need to be closely tracked.
22 | Third party claims that the technology we are using violates a patent or trade secret | Y | L | L | H | L | L | L | 9 | ● |  | ● | ● | Kret
110 | Project does not take appropriate steps to maintain confidentiality of Customer data | Y | L | L | M | L | L | L | 7 |  |  |  |  | Hull |  | Would affect company not necessarily the project
60 | Project Team not adequately trained in new processes & technology | Y | L | L | L | M | L | L | 7 | ● |  | ● | ● | Switala
51 | Installer commits crime/fraud in the field | Y | L | L | L | L | M | L | 7 | ● |  | ● | ● | Jamerson
50 | Safety incident occurs resulting in process change or training | Y | L | L | L | L | M | L | 7 | ● |  | ● | ● | Jamerson
40 | Contractor/sub-contractor fails DOE audit | Y | L | L | M | L | L | L | 7 | ● |  | ● | ● | Kret
18 | Interveners or grassroots groups negatively impact customer opinions | (SH) | L | L | L | L | L | L | 5 | ● |  | ● | ● | Sitkauskas
12 | DTE call center volume may increase due to 5,000 meter changes per day increasing wait time significantly | (SH) | L | L | L | L | L | L | 5 | ● |  | ● | ● | McCormick
91 | Negative media as a result of ineffective employment communications | Y | L | L | L | L | L | L | 5 | ● |  | ● | ● | Sitkauskas
67 | Communication plan with regulators is inadequate (does not explain benefits and detriments of the system) | Y | L | L | L | L | L | L | 5 | ● |  | ● | ● | Sitkauskas |  | Regardless of rating this issue should be tracked closely
66 | Communication plan with customers is inadequate (does not explain benefits and detriments of the system) | Y | L | L | L | L | L | L | 5 | ● |  | ● | ● | Sitkauskas |  | Regardless of rating this issue should be tracked closely
21 | Prolonged data center outage impacts AMI system | Y | L | L | L | L | L | L | 5 | ● |  | ● | ● | Melton
106 | Lack of effective Quality Management Plan | Y | [6 empty] | 0 | ● |  | ● | ● | Stasek |  | See # 88
93 | Project or vendor scope is not adequately defined | Y | [6 empty] | 0 | ● |  | ● | ● | Norlin |  | See # 88
88 | Inadequate project management | Y | [6 empty] | 0 | ● |  | ● | ● | Norlin |  | Need to expand
120 | [8 empty] | 0 | ● |  | ● | ●
119 | [8 empty] | 0 | ● |  | ● | ●
118 | [8 empty] | 0 | ● |  | ● | ●
117 | [8 empty] | 0 | ● |  | ● | ●
116 | [8 empty] | 0 | ● |  | ● | ●
115 | [8 empty] | 0 | ● |  | ● | ●
114 | [8 empty] | 0 | ● |  | ● | ●
113 | [8 empty] | 0 | ● |  | ● | ●
112 | [8 empty] | 0 | ● |  | ● | ●
Legend
[10 empty] | ● | Open Item
[10 empty] | √ | Completed Activity

## Chart Data (hidden)
Status | !OPEN
Count of Risk Event Description What is the event? | Column Labels
Row Labels | Green | Yellow | RED | Grand Total
Labor | 1 | 1 | 1 | 3
Tech |  | 3 |  | 3
Government | 1 |  |  | 1
(blank)
Grand Total | 2 | 4 | 1 | 7

## Score Defined
High = 5
Medium = 3
Low = 1
Total Score = (Schedule + Cost + Quality + Safety + Scope) x Likelihood

## Components of a risk (hidden)
Components of a Risk
•A Source of a risk or hazard – the thing which has the potential to harm or assist e.g. a dangerous chemical, competitors, government.
•An Event or Incident – Something that occurs such that the source of risk has the impact concerned e.g. a leak, competitor expands into or leaves your market, new or revised regulations, or some level of observation reaching a particular trigger level.
•A Consequence, outcome or impact on a range of stakeholders or assets e.g. environmental damage, loss or increase of market/profits, regulations increase or decreased competitiveness
•A Cause (what and why) for the presence of the hazard or the event occurring e.g. design, human intervention, funding, prediction or failure to predict competitor activity, failure to or expansion of market presence
•Controls and their level of effectiveness e.g. detection systems, clean up systems, policies, security, training, and market research.
•When could the risk occur and Where would it occur.

## List of Values (hidden)
H | ●
M | √
L
Life of Project
| 2010 | 2010 | 3
| 2010Q1 | 2011 | 3
| 2010 Q2 | 2011.0909 | 3
| 2010 Q3 | 20101201 | 3
| 2010 Q4 | 2010 Dec 1
| 2011 | 2010 Q1
| 2011 Q1 | 2010 Q2
| 2011 Q2 | 2010 Q3
| 2011 Q3 | 2010 Q4
| 2011 Q4 | 2011 12 01
2011 Q1
2011 Q2
2011 Q3
2011 Q4

## Rd 2 Directions (hidden)
1) | Major correction to wording ("wordsmithing" can be done later)
2) | Does this risk apply to all SmartCurrent projects (AMI, Smart Home, Smart Circuit)
3) | Identify Likelihood * |  | # of Risks Identified | 109 | 20
4) | Identify Impacts * |  | Available Time | 240 | 70
5) | Identify Owner |  | Minutes/Risk | 2.2018 | 3.5
* | Risk Plan is a living document - these ratings can/will change | 55.96%

## New Process Map (hidden)
Major Enterprise Projects | DRAFT: | <<Date>>
Project Risk Plan Management : Process Map
Project Manager / Risk Plan Manager
Project Stakeholders
Risk Owners
Financial Analyst
Scheduler
Monthly Update Coordinator
Begin Process
Identify Key Stakeholders
Plan and Schedule Risk Assessment
Conduct Risk Identification Session
Conduct Risk Quantification Session
Develop Risk Response Strategy
Develop Contingency Plan
Send out Request for Updates
Monthly Update Cycle
Integrate Identified Risks into Forecast
Integrate Identified Risks into Schedule
Incorporate Risks into Status Update
Compile Updated Risk Plan
Update Risk Plan
Update Risk Plan
Repeat Monthly Update Cycle Until Project is Complete
Provide Final Update to Risk Plan
File Risk Plan in Historical Archive
Monitor & Control Risks
Update Risk Plan
Publish Risk Plan
Review Industry/ Vendor Information for Lessons Learned & Project Specific Risks to Consider
Review Historical Risk Database For Related Risks
Review Current Projects for Related/Common Risks
Provide Input
Provide Input
Document Interdependencies in Work Scope