Earned Value Formulas

BAC = Budget at Completion (Project budget)

AC = Actual Cost of the Work Performed (ACWP)

EV = Earned Value (BCWP)

EV = Budgeted Cost of the Work Performed

EV = % complete times BAC

PV = Planned Value

PV = Budgeted Cost of the Work Scheduled (BCWS)

CV = Cost Variance

CV = EV – AC

CPI = Cost Performance Index

CPI = EV/AC

# Alternatives ETC = (BAC – BCWP) / CPI EAC = ETC + ACWP SV = Schedule Variance

SV = EV – PV

SPI = Schedule Performance Index

SPI = EV/PV

CSI = SPI * CPI

EAC = Estimate at Completion

EAC = BAC/CPI

ETC = Estimate to Complete

ETC = EAC – AC

VAC = Variance at Completion

VAC = BAC – EAC