## Slide 1: Risk Management Process Training Session
Victor Allen

## Slide 2: What are risks?
Project Management Institute definition of risk:
“an uncertain event or condition that, if it occurs, has a positive or negative effect on at least one project objective“ (i.e. scope, time, cost, quality, safety, etc…)

## Slide 3: What are risks?
My Definition of risk:
“A negative risk event is something that has not yet happened on your project, but if it did happen it would negatively impact your project to the extent that it would be worthwhile to reduce the likelihood that it will occur or reduce the negative impact if it occurred”
“A positive risk event is something that has not yet happened on your project, but if it did happen it would positively impact your project to the extent that it would be worthwhile to increase the likelihood that it will occur or increase the positive impact if it occurred”

## Slide 4: Risk/Issue/Action?
(Risk)
An undesirable event that has not yet happened
(Issue)
An undesirable event that has happened and needs attention
(Action)
Work that needs to be done

## Slide 5: Which of the following are risks?
The project may go over budget
I ran over a pot hole coming into work today and my tire is flat
Decisions in the site engineering area are not being made in a timely manner
Using unproven technology may require frequent re-design work resulting in a schedule delay

## Slide 6: Which of the following are risks?
The project may go over budget
This is more of an impact than a risk. There are many reasons why a project may go over budget. The real question is what are the things that would cause you to go over budget? The answer to this question is the risk. Here are some examples of a better way to write this risk statement:
It may take more time than planned to secure internal employees to work on this project which will require us to hire consultants resulting in a cost overrun on the project.
The contractor productivity level may be less than quoted in the contract resulting in a cost overrun.

## Slide 7: Which of the following are risks?
I ran over a pot hole coming into work today and my tire is flat
This is not a risk because it already happened. It has now become an issue that you have to deal with. Time to execute your contingency plan – hopefully you have a spare or AAA.

## Slide 8: Which of the following are risks?
Decisions in the site engineering area are not being made in a timely manner
This is not a risk because it already happened. Decisions are already not being made timely, so the risk has occurred. It has now become an issue that you have to deal with.

## Slide 9: Which of the following are risks?
Using unproven technology may require frequent re-design work resulting in a schedule delay
This is a risk.

## Slide 10: 5 Characteristics of a Risk Event
Risk is clear and understandable to anyone who reads it
Risk describes the impact or “so what” factor
Risk has not yet happened
Risk is something your actually worried about.
Risk affects your project, not another project or the company in general

## Slide 11: Why do we manage risks?
To improve our chance of project success
  Meeting your objectives
  Meeting your budget
  Meeting your schedule
  Working Safely
  Delivering with quality
  Satisfying your customers and stakeholders
  Avoid surprises
“The first step in the risk management process is to acknowledge the reality of risk. Denial is a common tactic that substitutes deliberate ignorance for thoughtful planning” ~ Charles Tremper
“If you don’t manage the risks, the risks will manage you” ~ Victor Allen

## Slide 12
Program Risk Manager
Project Risk Manager(s)
Project 1
Project 2
Project 3
Risk Management Database
Risk Register
Risk Assessment Reports
Risk Scorecard
Processes and Methods
Risk Response Planning
Mitigation Planning
Contingency Planning
Reviews
External
Audit
DOE
Expert
Internal
Corporate Risk
General Audit
Compliance
Risk Management Framework

## Slide 13: The Risk Register
Project X: Risk Plan |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | Impacts |  |  |  |  |  |  | 
# | Risk Event Description What is the event? | Category Sub-project, Project Phase, Location etc. (Optional) | Likelihood | Schedule | Cost | Quality | Safety | Scope | Total Score | Risk Event Drivers What are the conditions, actions, or events that are likely to trigger the risk event to occur or is a leading indicator to the risk event occurring? | Response/ Mitigation Strategy What action(s) will be taken to limit the likelihood of these event occurring or limiting the impacts?
1 | Contracted vendor under performs resulting in schedule delays, rework and cost overruns | Contract | H | H | M | M | M | L | 75 | Drivers to monitor: - Schedule slippages and missed milestones. Drivers that have occurred: - Re-work occurring. - Change orders issued. | Planned Actions: - Conduct weekly monitoring of schedule adherence. - Implement change review process to manage scope, time, cost changes effectively. - Develop and implement quality management plan for vendor work. Completed Actions: - Negotiate cost plus incentive fee contract based upon milestone completion

## Slide 14: Risk Register – Impacts Defined
Risk impact level Matrix |  |  |  |  |  |  | 
Likelihood | Low |  | Medium |  |  | High | 
 | Unlikely |  | Likely |  |  | Almost Certain | 
Impacts | Low |  | Medium |  |  | High | 
Schedule | No Impact to Critical Path or Field Work |  | Potential to Affect Critical Path or Field Work |  |  | Certain to Affect Critical Path or Field Work | 
Cost | Less Than | $ 250,000 | $ 250,000 | to | $1,000,000 | Greater Than | $ 1,000,000
Quality | Minor impact to product deliverables |  | Moderate impact to product deliverables |  |  | Major impact to product deliverables | 
Safety | No Impact to worker safety |  | Minor impact to worker safety |  |  | Major impact to worker safety | 
Scope | < 1% |  | 2% to 5% |  |  | > 5% | 

## Slide 15: Responding to Risks
Risk: I may run out of gas on my way to work in the morning and be late for an important meeting which will make my boss very angry.
What are you going to do to respond to this risk?
Responding to a risk mean that you are going to try one or more of the following:
Mitigate the risk: try to reduce the likelihood it will occur and/or the impact if it occurs (i.e. fill up your tank with gas the night before).
Transfer: give some or all of the risk to a third party (i.e. hire a cab)
Avoid: Eliminate the possibility (i.e. walk to work or stay at nearby hotel)
Accept: Do nothing and take your chances

## Slide 16: The Risk Register
# | Risk Event Description What is the event? | Contingency Plan What action(s) will be taken if this event occurs? | Owner | Risk Timeframe Critical date(s) or period of exposure | Organizational or Cross-Project Impacts | Comments
1 | Contracted vendor under performs resulting in schedule delays, rework and cost overruns | - Negotiate contract with alternate vendor to perform services. - Complete work with internal resources. | Jane Doe | On-going | No | (01/12) Vendor has repeatedly failed weld inspections on structural steel.

## Slide 17: The Risk Register
 |  | Financial Analysis |  |  |  |  |  | 
# | Risk Event Description What is the event? | FA Review Required? | $ Impact | Source | Probability | Source | EMV | Comments
1 | Contracted vendor under performs resulting in schedule delays, rework and cost overruns | Y | $ 500,000 | PM input | 0.9 | Default | $ 450,000 | 

## Slide 18: The Risk Register
 |  | Schedule Analysis |  |  |  | Risk Closure | 
# | Risk Event Description What is the event? | Scheduler Review Required? | Critical Path ? | Scheduler Response\ | Comments (Activity #, Quantified impact etc.) | Closure Statement | Notes / Lessons Learned
1 | Contracted vendor under performs resulting in schedule delays, rework and cost overruns | Y | This risk will impact the Critical Path | Built 20 days of contingency into the Schedule | Steel Erection Work Package delays will impact Siding and Roof Construction Work Packages. |  | 

## Slide 19: Tips for Successful Risk Management
Executive Champion who understands Risk Management
Risk Manager who owns process, coaches and mentors
Good set of processes, tools, and templates
Risk Training for the team (concept and processes)
Make Risk Management a priority
Benchmark your process and effectiveness regularly
Establish Historical Risk Database and leverage the past
Work the Risk Plan
Develop Contingency Plans for high risk items
Don’t sweat the small risks