## Slide 1
Ideal State
Gap to be Corrected
Problem/Project Statement
Major Risks Identified
Current State
Case for Change
Key Business Assumptions
Performance Criteria | Current | Target
Duration time | 24 hrs. | 48 hrs.
Activation time | 1 hr. | 30 min.
Reduction of Common Side effects | 25% | 50%
Scope Statement
1
3
4
2
Key Project Milestones | Date
Drug and technology research and development | 11/22/18
Patient survey and survey analysis | 02/12/19
Clinical trial approval | 11/27/20
Drug interaction studies | 01/30/21
FDA Approval | 11/20/21
Project Charter
To have created a viable insulin therapy alternative, one that itself can be iterated upon and introduce new avenues of therapy. Having any and all accomplished in this project contribute to the furtherance of diabetes treatment regardless of the ultimate success of this project.
Patient ability to change lifestyle habits may assist in a positive reaction to the drug. Developing a drug that will be well tolerated by an acceptable portion of the population.
Total Estimated Project Cost = 200,000,000
Patent violations (drug)
Copyright violations (software)
FDA denial
The effectiveness of medical therapies is intrinsically tied to a patients capability to abide by a requisite lifestyle regimen. Current insulin therapies are varied to fulfill the specific needs of individuals with diabetes; however, no treatment can be a one-size-fits-all and there are still gaps present even among the present range of treatment options.
Drug production will be in-house pending client approval
Cost of drug development will be approved by client.
Approval | Init | Date
Client: Victor Allen |  | 
Platform Manager/Director: |  | 9/16/2018
There is continued need for research and advancement in diabetes medicine for the sake of public health as present solutions still prove insufficient for many people.
The development of a new insulin drug, along with a survey of both biological and lifestyle gaps with present diabetic treatments will be completed. An assessment of the practical avenues in potential alternatives in treatment to reconcile these apparent lapses as well as assessing concurrent research projects. In-house exploration of potential treatment alternatives including lab testing, technology research and development, and clinical trials will be performed.
Developing an insulin therapy alternative for those in need. One that also strives to mitigate common side effects and improves upon quality of life, so as long as the patient is willing an able to adapt to a requisite lifestyle regimen.
Organizational Impacts
Addressing the necessity of technological research relative to the findings of the patient survey.
Client:Victor Allen
Project: Pharmaceutical Drug Development
Date: 9/14/18 Revision: 10/6/18

## Slide 2
Excluded from Scope
Included in Scope
Project Charter
5
6
Facilities and equipment: The facility and equipment will be supplied by the in-house pharmaceutical company, if the client agrees to the terms. The facility will supply all of the equipment that is needed in production, and clinical trials of the drug.
Financial resources: Financial resources will be supplied by the client that has hired the company to produce the drug. The terms for the allocation of the funds, will be discussed by the client and the pharmaceutical company.
Marketing: The decision as how to market the drug will be discussed by both parties and the agreed upon marketing firm will present its marketing strategies to both parties, however, the final decision will be that of the clients.
Mass Production of drug: Mass production of the drug will depend on the clinical trials being successful and the approval by the FDA for the drug. A positive outcome of both of these factors are expected, and will be beneficial to how the company and the client agrees on the mass production details of the drug.
National diabetes patient survey: Source of latter research and advances in medical science. The survey will consist of a variety of questions that will assist in the development of the drug.
Review of survey information and other contemporary studies: Does treatment and test work, and are they efficiently delivered. What are the positive and or negative responses that will help to formulate viable results. The comparison study will eliminate duplicate studies and trial and error mishaps and or copyright infringement.
Drug research and development: What gaps in health may drive additional questions for research. The change in patient life style may assist in the drugs effectiveness. Attempts to develop a drug, that may be viable to a greater percentage of the population; with the understanding that the drug may not be affective for all patients, we hope to reduce the negative affects for a larger percentage of the population.
Software development for biological monitoring: Track test and research treatment into transferable data. Developing software that will help in the development of the drug, and to track the results, in an effect to productively monitor data results.